## DD_Session_Status (hidden)
Transition Phase | Capability | Unit | 2021-09-01 |  | 2021-09-02 |  | 2021-09-03 |  | 2021-09-06 |  | 2021-09-07 |  | 2021-09-08 |  | 2021-09-09 |  | 2021-09-10 |  | 2021-09-13 |  | 2021-09-14 |  | 2021-09-15 |  | 2021-09-16 |  | 2021-09-17 |  | Total
|  |  | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed
Due Diligence & Discovery Phase | HR_Legal_R&E | K-C | 1 | 1 | 2 | 2 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  | 1 |  | 1 | 1
|  | Incumbent | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 2 | 2 | 0 |  | 1 | 1 | 1
Knowledge Transition | HR_Legal_R&E | K-C
Incumbent
Shadow Support | HR_Legal_R&E | K-C
Incumbent
Primary Support | HR_Legal_R&E | K-C
Incumbent

## Session Statistics (hidden)
|  |  |  | 2021-09-20 |  | 2021-09-21 |  | 2021-09-22 |  | 2021-09-23 |  | 2021-09-24 |  | 2021-09-27 |  | 2021-09-28 |  | 2021-09-29 |  | 2021-09-30 |  | 2021-10-01 |  | 2021-10-04 |  | 2021-10-05 |  | 2021-10-06 |  | 2021-10-07 |  | 2021-10-08 |  | 2021-10-11 |  | 2021-10-12 |  | 2021-10-13 |  | 2021-10-14 |  | 2021-10-15 |  | 2021-10-18 |  | 2021-10-19 |  | 2021-10-20 |  | 2021-10-21 |  | 2021-10-22 |  | 2021-10-25 |  | 2021-10-26 |  | 2021-10-27 |  | 2021-10-28 |  | 2021-10-29 |  | 2021-11-01 |  | 2021-11-02 |  | 2021-11-03 |  | 2021-11-04 |  | 2021-11-05 |  | 2021-11-08 |  | 2021-11-09 |  | 2021-11-10 |  | 2021-11-11 |  | 2021-11-12 |  | 2021-11-15 |  | 2021-11-16 |  | 2021-11-17 |  | 2021-11-18 |  | 2021-11-19 |  | 2021-11-22 |  | 2021-11-23 |  | 2021-11-24 |  | 2021-11-25 |  | 2021-11-26
Wave | Applications | Total Planned Sessions | Total Sessions Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed | Planned | Completed
Wave 1 - Workday | Workday | 0 | 0
Wave 1 - Workday | Workday Recruiting Module | 0 | 0
Wave 1 - Workday | ASK HR | 0 | 0
Wave 2a - In-house Developed | Internet HR | 0 | 0
Wave 2a - In-house Developed | Onboarding Form | 0 | 0
Wave 2a - In-house Developed | K-C & Me | 0 | 0
Wave 2a - In-house Developed | Competency Portal | 0 | 0
Wave 2a - In-house Developed | Corporate Records | 0 | 0
Wave 2a - In-house Developed | HR Medical Databases (SAS) | 0 | 0
Wave 2a - In-house Developed | HR Team Web | 0 | 0
Wave 2a - In-house Developed | HR Unsubscribe | 0 | 0
Wave 2a - In-house Developed | Intranet AP Evaluation and Competency | 0 | 0
Wave 2a - In-house Developed | Intranet LAO flujosaprobacion | 0 | 0
Wave 2a - In-house Developed | Non-Disclosure Agreement (NDA) | 0 | 0
Wave 2a - In-house Developed | Stock Ownership | 0 | 0
Wave 2b - Packaged Software, SaaS | ATmyHR Portal | 0 | 0
Wave 2b - Packaged Software, SaaS | APDATA-LAO | 0 | 0
Wave 2b - Packaged Software, SaaS | Exactus | 0 | 0
Wave 2b - Packaged Software, SaaS | Anaqua IP Management System | 0 | 0
Wave 2b - Packaged Software, SaaS | Benson (audiometer) | 0 | 0
Wave 2b - Packaged Software, SaaS | Codeas ASOKIM | 0 | 0
Wave 2b - Packaged Software, SaaS | Exterro eDiscovery | 0 | 0
Wave 2b - Packaged Software, SaaS | Exterro Gateway Coordinator | 0 | 0
Wave 2b - Packaged Software, SaaS | HR Health Services ARM - CAD | 0 | 0
Wave 2b - Packaged Software, SaaS | HR HealthCalc | 0 | 0
Wave 2b - Packaged Software, SaaS | HR Occupational Health Manager (OHM) | 0 | 0
Wave 2b - Packaged Software, SaaS | HR OMI Spirometry | 0 | 0
Wave 2b - Packaged Software, SaaS | Legal Entity (BluePrint) | 0 | 0
Wave 2b - Packaged Software, SaaS | Milestone | 0 | 0
Wave 2b - Packaged Software, SaaS | OnGuard | 0 | 0
Wave 2b - Packaged Software, SaaS | PCT Safe | 0 | 0
Wave 2b - Packaged Software, SaaS | Quest (blood draws) | 0 | 0
Wave 2b - Packaged Software, SaaS | reDiscovery | 0 | 0
Wave 2b - Packaged Software, SaaS | SkillSoft Training | 0 | 0
Wave 2b - Packaged Software, SaaS | SpecManager Time and Attendance | 0 | 0
Wave 2b - Packaged Software, SaaS | Therefore Scanning - Australia | 0 | 0
Wave 2b - Packaged Software, SaaS | Therefore Scanning - China | 0 | 0
Wave 2b - Packaged Software, SaaS | Digital Sentry Control Point | 0 | 0
Wave 2b - Packaged Software, SaaS | HRIS Payroll - Hongkong | 0 | 0
Wave 2b - Packaged Software, SaaS | HRIS Payroll - Korea | 0 | 0
Wave 2b - Packaged Software, SaaS | HRIS Payroll - Taiwan | 0 | 0
Wave 2b - Packaged Software, SaaS | Access Control (Continuum) | 0 | 0
Wave 2b - Packaged Software, SaaS | Corporate Benefits - Andean | 0 | 0
Wave 2b - Packaged Software, SaaS | Electronic Paystub | 0 | 0
Wave 2b - Packaged Software, SaaS | FOCA - Payroll | 0 | 0
Wave 2b - Packaged Software, SaaS | HR Polar Trift BodyAge System | 0 | 0
Wave 2b - Packaged Software, SaaS | HRIS Payroll - Vietnam (LacViet) | 0 | 0
Wave 2b - Packaged Software, SaaS | Indonesia Absence Management | 0 | 0
Wave 2b - Packaged Software, SaaS | Intranet LAO ANDEAN HR | 0 | 0
Wave 2b - Packaged Software, SaaS | Platinum Mobile | 0 | 0
Wave 2b - Packaged Software, SaaS | Time and Attendance - Etivity - Australia | 0 | 0
Wave 2b - Packaged Software, SaaS | Time and Attendance - Thailand | 0 | 0
Wave 2b - Packaged Software, SaaS | Time Management - Malaysia | 0 | 0
Wave 2b - Packaged Software, SaaS | Adaptive Insights | 0 | 0
Wave 3 - Research & Engineering | 3DExperience | 0 | 0
Wave 3 - Research & Engineering | Advantics-Monitor Plus | 0 | 0
Wave 3 - Research & Engineering | Adviews-Ad Intel | 0 | 0
Wave 3 - Research & Engineering | ARM Cortex-M | 0 | 0
Wave 3 - Research & Engineering | Aspera | 0 | 0
Wave 3 - Research & Engineering | AutoCAD | 0 | 0
Wave 3 - Research & Engineering | AutoCAD Electrical | 0 | 0
Wave 3 - Research & Engineering | BazaarVoice | 0 | 0
Wave 3 - Research & Engineering | Brand Hub | 0 | 0
Wave 3 - Research & Engineering | Clang CRM Magento | 0 | 0
Wave 3 - Research & Engineering | Consumer Services Department Web Interface | 0 | 0
Wave 3 - Research & Engineering | Dassault DraftSight CAD | 0 | 0
Wave 3 - Research & Engineering | Digital Visual Management (IObeya) | 0 | 0
Wave 3 - Research & Engineering | Dispenser Tool | 0 | 0
Wave 3 - Research & Engineering | Drawing and Release Control System (DRCS) | 0 | 0
Wave 3 - Research & Engineering | Events at K-C | 0 | 0
Wave 3 - Research & Engineering | Explorer Direct | 0 | 0
Wave 3 - Research & Engineering | Gen Video | 0 | 0
Wave 3 - Research & Engineering | Lab Pump Controller | 0 | 0
Wave 3 - Research & Engineering | Modeling Data Management Platform | 0 | 0
Wave 3 - Research & Engineering | Open Design Alliance (ODA) | 0 | 0
Wave 3 - Research & Engineering | Panopto Video Platform | 0 | 0
Wave 3 - Research & Engineering | PlotPDF | 0 | 0
Wave 3 - Research & Engineering | R and E Search Tool | 0 | 0
Wave 3 - Research & Engineering | Seamless Innovation Management Platform | 0 | 0
Wave 3 - Research & Engineering | Research Files Online | 0 | 0
Wave 3 - Research & Engineering | Survey Gizmo | 0 | 0
Wave 3 - Research & Engineering | SoftArtisans | 0 | 0
Wave 3 - Research & Engineering | SolidWorks | 0 | 0
Wave 3 - Research & Engineering | World Clock-Time Zones Mobile App | 0 | 0
Wave 3 - Research & Engineering | Work Request Portal | 0 | 0
Wave 3 - Research & Engineering | SolidWorks | 0 | 0
Wave 3 - Research & Engineering | Transformation and Innovation Planning | 0 | 0

## KT - Azure
Knowledge Transfer | Azure - Linux | [6 empty] | 0%
Total No Of Hours |  | 60
Headers | Key Topics | No Of Hours | TechM SME | Atos SME | Centrient SPOC | KA Start Date | KA End Date | Progress %age | Links | Remarks / Challeges / Questions
Project Overview | Understand Current Environment and Infrastructure Walk through of Documents Subscription details Environment details Application Details Vendor Support & other like shift support details Scope of work with respect to Azure Cloud | 2 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
Azure/Platform | HLD of Azure environment | 3 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| LLD of Azure environment |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| SOP Docs for Azure environment |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Runbooks for Windows/Linux environment |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
Azure | Azure Introduction and overview | 3 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Security |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Virtual Instances |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Documentation |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Disaster Recovery |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Vendor Management |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
Azure Native Monitoring | Collect- Metrics, Log Analytics Visualize and analyze- Dashboard Alert configaration based on the Threshold How is server monitoring performed? What all is being monitored currently and what is the priority of different types of alerts. Any exclusions from monitoring Various thresholds for monitoring. Any exceptions to monitoring? Any console available for team to view live alerts POC for alerts and standard procedure/processes to be followed in case of P1 & P2 issues Are monitoring tickets generated automatically? Process/doumentation for handling monitoring alerts | 2 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
Azure Key Vault/Encryption/Service accounts | Where are these services account used is it for any application or servers. | 2 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Will require the services account details with credentials. |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Details on Key vaults and encryption used in environment |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Do we have any specific group policy for these service account |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Please provide the naming convention used for the service accounts. |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
Azure Backup | Back up a Virtual Machine Recovery services Vault Backup policy Backup retention policy Backup and recovery (tools and technology being used) Backup and restore process | 2 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
Azure Network | Landing Zone, Bastion Host, Jump Server, Network Connectivity & high level Architecture VPN & Firewall Gateways,Connections, Network vendor and line details | 2 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
Storage | Storage Overview Blob storage Storage account Encription W.r.t Bring your own key (BYOK) Storage account access methodology(Shared service access storgae account, Secret Keys etc..) Log Analytics Details | 2 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
Compute | Virtual Machines Deployments & other details,Vnets,Subnets,Azure load Balancer..etc Virtual Machine scale sets AKS | 2 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
Azure Security Center | Policies, Score, Day to day jobs | 4 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
SIP and Value added already done | Tracker of SIP and Value added | 1 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
DR / BCP/ Resillence | RPO / RTO values / Default RPO / RTO Values | 2 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| DR Sites / How DR is done / Frequencey / DR Drill |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Application participating in DR |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Recovery Time objective / Recovery Point Objective of DR applications |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| SLAs during DR period |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Is DR testing done on every new application roll-out (specific to that application) |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Windows Infrastructure services or Application running on Windows that are always active in DR |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Existing Issues, Risk and Gaps with DR and BCP |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| DR Locations for various sites |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
Vendor Management | Vendor Management process/Contract document,Discussion with Other App vendors/Suppliers | 1 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Vendor Contacts & SLA |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Vendor Support Escalation Matrix |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
License Management | When servers are decommissioned, how the License are retained, Briefly understand the process,Do we use Azure BYOL or use the OS licensing from azure,if we use BYOL , please provide details for the KMS server in use. | 1 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Contact details of License owners, Globally, License/Certificates Management |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| How the new software purchase model works |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
Azure Patch Management if applicable required (OS patching will be taken care by Infra team) | Overview of Patching tool, function and dependecies Patch mgmt process-Decision on installation of patches, Selection of Patches / Reporting,Troubleshooting with Installed patches, Troubleshooting of different Error Codes if problem is related to windows client Patch process with Release Management team Patch server Administration / Script Customisation Server grouping towards patch Presence of Global Patch servers Patch Architecture Pre and Post deviation process in Patching Support team and Security team handshake process Exceptions on Patching process How windows clusters are being patched. Frequency of patch roll-out Sequence of Patch installation (Non Prod , Prod) Do you have any requirement that one part of the production environment should be patched before another? Presence of Test environment for Patches How the Patches are assessed Emergency Patch deployment process Server Downtime window How the Patch roll back is done How the Server restart is stopped / halted towards Server patching What are GPO and Registry changes done on clients for Patch pro cess Patch calender for Critical and no Critical Infrastructure (Prod and Non Prod) | 3 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
Process | Any process being followed for Capacity Management | 5 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Incident Management |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Change Management |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| CMDB Management |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Problem Mangement |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Escalation Matrix |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| OnBoarding / Offboarding Management |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Documentation |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| High Level overview of IM/CM/PM Process |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Change Communication Process |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Change Control Approval (CAB) Details |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Incident Response/Resolution Time-lines |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Change Freeze Calendar |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Daily/Weekly/Quarterly/Yearly Review Meetings |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Process to handle planned down-time like Patching and Rebooting of Tools Services |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Tools Server and Services Restart policies for Scheduled Maintenance |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| SEV1/SEV2/SEV3/SEV4 Ticket Discussion |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Current Outage Handling Process for these Tools |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| All Critical SEV1/SEV2 ticket dump analysis with permanent resolution (RCA Documentation) |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| List of Segregated Critical Tools (per SLAs (Gold,Silver,Platinum Standards)) (If Applicable) |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Details of SOX/Other Compliance & Audit |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Current procedure to demonstrate data to the auditor on quarterly or on Demand basis for all SOX compliance Tools/Data |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Special Event Coverage for these Tools (If Applicable) |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Overview on existing Problem management process |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Known/persistent issue details;Major Infra agents issues that occurred frequently |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Process of identifying problem from repetitive Incidents |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Escalation process after Identifying problem |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Overview of Service request and workflow process |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
Antivirus | Please provide the details of the Antivirus used for the environment | 5 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Where is Antivirus master server located. |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Who is Currently managing the Antivirus. |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| What is the version and Antivirus Update Strategies |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| How are the new build servers getting the Antivirus installed. |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| How is the Antivirus Licensing Managed for Client as well for the servers. |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| How is the Antivirus Licensing Managed for Client as well for the servers. |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
Application Mappings / Vendor | Deepdrive on Applications installed on Windows | 3 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Understand Application Environment / Application mapping with Inventory |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Schematic Diagrams of Application |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Application owner info / Escalation Matrix / Installation procedures |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Scripts running on Windows / File Exclusion for AV |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Challenges / Leagacy apps / Outage Window |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Business Slowdown / Peak Business window |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
Tools & Scripts | System Management Tool,Maintaining & troubleshooting scripts | 3 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Password Management Tool |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Server Monitoring tools & Threshold Prameters configured |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Backup Tools /Agent installed & support scope of wintel |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Tool used for Vulnerablility scanning and dependency of wintel track |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Health check Procedures/Documents/Scripts |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Tools useded in day to day operations;Performance and Fine Tuning of Servers : Process Performance and Fine Tuning of Servers : Tools used Reports generated |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Patch Management Tool Wintel Scope |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Server Build Image build tool & Wintel Scope |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Network Management Tools like (SMS/SCCM) existance & Wintel track scope |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Standard scheduled /batch job over wintel server |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
Azure IP/DHCP Management | Existing IP/DHCP inventory | 3 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| IP address and reservation details/process |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Network team escalation matrix |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Default lease duration |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Documentation of IP management |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
Inventory Classification | Server naming conversion segment wise | 3 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Baseline Inventory list with complete server details (App/owner/warranty) |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
| Risk and issues with respect to Asset |  | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
OS Admin Task related to cloud | Introduction and overview Inventory Architectural & Design Overview of Wintel/Linux Environment Business Applications and Wintel/Linux Environment Dependencies Inventory collection / CMDB Discussions (H/W & OS Landscape) Existing Critical Windows Runbook and SOPs Understanding the Team Structure; Roles and Responsibilities Understanding the Risk/Issue/Assumption/Dependencies for on-going support infrastructure (KEDB) Discussion on Various Tools (scripting/ automated) in use Software/ OS Repository Details Password details (Shared/standalone) Tool used for Password Management Overview on Event notification tools and procedures Customer Escalation Matrix Known/persistent issue details Please provide the naming convention for the servers that are build. Do we have the Images for the Linux and Windows VM's. Do we update the image every 2 months with the latest patches and maintain a versioning for the same. Are we following all CIS standard. Is the image hardening applied on the VM Image or they are pushed by GPO once the server is built and joined to domain. Server domain joining procedure Provide the extract of the policy which is set up. Are there any specific application ports and protocol being open/closed using the policy. Do we have any specific requirments for the application of the Hardening standards. Server Installation Procedure & checklist Standard followed for OS configurations (Partioning/ Page file) File system Configuration Operating System Customization for Application Startup & Shutdown scripts setup & administration Complete Server Configuration document - Checklist Compliance Management/Server Hardening Tools Installation / Agent Local Administrator name and other Local account names Server Build and Configuration standards (Comissioning /Decomissioning) Server Rebuild in the event of Failures (Refernce docs/Dependency/Process),DR / BCP/ Resillence,Windows Patch Management | 6 | Satya Krishna | Anoop CR | Pranav /Rowald | 2022-11-21 | 2022-12-30 | 0%
|  |  |  | Anoop CR |  |  |  | 100%

## SME - Holiday Tracker
Organisation | Associate Name | Technical Tower | Holiday Start | Holiday End | No Of Days
Note on A1: Saurabh Nandavar: TechM ATOS Centrient