## Contact Details
Project Name - NANT Media
Team Contact List
Title | Name | Email ID | Mobile Number
India Delivery Lead | Sujit Thipse | Sujit Thipse <st0010943@TechMahindra.com>
Delivery Lead (Onsite) | Nihar Parikh | Nihar Parikh <NP003646@TechMahindra.com>
Transition Manager | Kaushik Sirole | Kaushik S2 <KS00844161@TechMahindra.com> | 90084 88677
TechM Shared Services Lead | Vivek Chaudhary | Vivek Kumar129 <VK00842101@TechMahindra.com>
Business Apps | Vishwas Salunke Avijit Waghmare | Vishwas Salunke <vs0013106@TechMahindra.com>; Avijit Waghmare <AW00492399@TechMahindra.com>
EUC | Naresh Manne | Naresh Manne <NM00725172@TechMahindra.com>
Service Desk | Ashutosh Singh | Ashutosh Singh3 <AS00618307@TechMahindra.com>
SSC Ops Mgr | Akshay Malhotra | Akshay Malhotra <AM00885218@TechMahindra.com>
Azure Cloud | Pankaj Kumar Agrawal Viswanathan Gopalakrishnan | Pankaj Kumar Agrawal <PA00901387@TechMahindra.com>; Viswanathan Gopalakrishnan <VG00761236@TechMahindra.com>
Network | Dhanesh Ramchandra | Dhanesh Ramchandra <DK00887408@TechMahindra.com>
India Program Manager | Mandar Kulkarni | Mandar Kulkarni <mandarku@TechMahindra.com>
Program Director (Onsite) | Sumangala Ambala | Sumangala Ambala <sambala@TechMahindra.com>
Governance & SLA Manager | Hemant Agarkar | Hemant Agarkar <agarkar@TechMahindra.com>
TechM Infra lead | Munir Khan (ICS) | Munir Khan <munirk@TechMahindra.com>

## Summary
Track | Technology | KT Calendars | KAP documents | Reviewed by TechM | Number of KT sessions planned (Incumbent) | Number of KT sessions completed | %age of Knowledge Transfer completion | Readiness for Support | Remarks
SSC Infra Support | AD, DNS | [6 empty] | 1. KT Status- 2. Resource readiness- 3. Access Status-
| Exchange/ Messaging | [6 empty] | 1. KT Status- 2. Resource readiness- 3. Access Status-
| Windows & HyperV | [6 empty] | 1. KT Status- 2. Resource readiness- 3. Access Status-
| Storage | [6 empty] | 1. KT Status- 2. Resource readiness- 3. Access Status-
| Backup (TSM) | [6 empty] | 1. KT Status- 2. Resource readiness- 3. Access Status-
| Linux | [6 empty] | 1. KT Status- 2. Resource readiness- 3. Access Status-
| AS400 | [6 empty] | 1. KT Status- 2. Resource readiness- 3. Access Status-
| Oracle- DBA | [6 empty] | 1. KT Status- 2. Resource readiness- 3. Access Status-
| SQL Server | [6 empty] | 1. KT Status- 2. Resource readiness- 3. Access Status-
| EUC | [6 empty] | 1. KT Status- 2. Resource readiness- 3. Access Status-
| Infra Monitoring | [6 empty] | 1. KT Status- 2. Resource readiness- 3. Access Status-
| BigFix / Patching | Confirmed | Shared |  | 5 |  | 0%
| SIEM / Security | Confirmed | Pending for Security |  | 5 |  | 0%
B37B30:DB30:D41

## AD, Windows
Domain | Topics | Sessions | Week | Date | Actual Date | Schedule Start Time | Schedule End Time | Session Duration | TechM Spoc | LA Times Spoc Detail | Staus | Comments | Scheduled
AD | AD architecture (Forest and Domain information) | Session1 | 1 | 2022-09-15 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi |  |  |  | Completed
AD | Configuration and validation of DNS Server Work Flow (AD Integration , Forwarder, Root hints) | Session1 | 1 | 2022-09-15 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi |  |  |  | Ongoing
AD | Role & configuration of DHCP Server (IP Range & subnet details) | Session1 | 1 | 2022-09-15 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi |  |  |  | Hold
AD | Configuration of AD replication Site and Services details | Session1 | 1 | 2022-09-15 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi |  |  |  | Pending
AD | Configuration list of Group policy | Session2 | 2 | 2022-09-18 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi |  |  |  | Not Started
AD | File & Folder permission overview (NTFS, NFS) | Session2 | 2 | 2022-09-18 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi
AD | Service Account Details | Session2 | 2 | 2022-09-19 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi
AD | Datacenter & DR support Overview | Session2 | 2 | 2022-09-19 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi
AD | Escalation Matrix | Session2 | 2 | 2022-09-20 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi
AD | Current Plan or Strategy on nearing EOS/EOL products | Session3 | 2 | 2022-09-20 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi
AD | ITSM - Change Management, Incident, Problem, etc Overview | Session3 | 2 | 2022-09-20 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi
AD | Monthly reports requirement | Session3 | 2 | 2022-09-20 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi
AD | P1 Call – Process | Session3 | 2 | 2022-09-21 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi
AD | Configuration & details of Print Server( Add & remove printer, Drivers) | Session3 | 2 | 2022-09-21 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi
AD | Details of backup tool used for Domain controller, Windows File & Print Server (Native / 3rd party tool) | Session4 | 2 | 2022-09-21 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi
AD | New Server Deployment Overview | Session4 | 3 | 2022-09-21 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi
AD | Server Standards, Naming convention | Session4 | 3 | 2022-09-22 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi
AD | Audit Requirement and compliance report | Session4 | 3 | 2022-09-22 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi
AD | Server User Management and Policies | Session4 | 3 | 2022-09-22 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi
AD | Server Decommission Process | Session5 | 3 | 2022-09-25 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi
AD | Recap & Review | Session5 | 3 | 2022-09-25 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi
AD | Activities handled Daily/Weekly/Monthly/Quarterly support services and status reports | Session5 | 3 | 2022-09-26 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi
AD | Q & A | Session6 | 3 | 2022-09-27 |  | 10:00 | 12:00 | 2 Hrs | Ali Mehndi
AD
AD
AD
AD
AD
AD
AD
AD
AD
AD
AD
AD
AD

## VMWare HyperV
Domain | Topics | Sessions | Week | Planned Date | Actual date | Schedule Start Time | Schedule End Time | Session Duration | TechM Spoc | LA Times SPOC Spoc Detail | Staus | Scheduled
VmWare | Introduction, Hyper V Infra details | Session1 | Week 1 | 2022-09-15 |  | 14:00 | 15:00 | 1 hour | Gattu Guruprasad |  |  | Completed
VmWare | Hyper-V Cluster details | Session1 | Week 1 | 2022-09-15 |  | 14:00 | 15:00 | 1 hour | Gattu Guruprasad |  |  | Ongoing
VmWare | New VM creation/ISO location | Session1 | Week 1 | 2022-09-18 |  | 14:00 | 15:00 | 1 hour | Gattu Guruprasad |  |  | Hold
VmWare | Disk expansion Steps/expalined about online/Offline activity | Session1 | Week 1 | 2022-09-18 |  | 14:00 | 15:00 | 1 hour | Gattu Guruprasad |  |  | Pending
VmWare | Cluster Shared Volume/SAN details | Session2 | Week 1 | 2022-09-19 |  | 14:00 | 15:00 | 1 hour | Gattu Guruprasad |  |  | Not Started
VmWare | Virtual Networks in Hyper V Infra | Session2 | Week 1 | 2022-09-19 |  | 14:00 | 15:00 | 1 hour | Gattu Guruprasad
VmWare | Live Migration/Quick Migration/Storage Migration | Session2 | Week 2 | 2022-09-20 |  | 14:00 | 15:00 | 1 hour | Gattu Guruprasad
VmWare | Ongoing Critical Incidents | Session3 | Week 2 | 2022-09-20 |  | 14:00 | 15:00 | 1 hour | Gattu Guruprasad
VmWare | Change Management/catageries | Session3 | Week 2 | 2022-09-21 |  | 14:00 | 15:00 | 1 hour | Gattu Guruprasad
VmWare | Decommision process of VM | Session4 | Week 2 | 2022-09-22 |  | 14:00 | 15:00 | 1 hour | Gattu Guruprasad
VmWare | P1 management and process of Escalation metrics | Session4 | Week 2 | 2022-09-22 |  | 14:00 | 15:00 | 1 hour | Gattu Guruprasad
VmWare | Recap & Review | Session5 | Week 2 | 2022-09-26 |  | 14:00 | 15:00 | 1 hour | Gattu Guruprasad
VmWare | Q & A | Session5 | Week 2 | 2022-09-26 |  | 14:00 | 15:00 | 1 hour | Gattu Guruprasad
VmWare | KAP Documents Review | Session6 | Week 2 | 2022-09-27 |  | 14:00 | 15:00 | 1 hour | Gattu Guruprasad
VmWare | KAP Document signoff | Session7 | Week 2 | 2022-10-01 |  | 14:00 | 15:00 | 1 Hour | Gattu Guruprasad

## AZURE
Project Name: Centrient
Transition Unit | SME Name | KT Receiver | Knowledge Area | Description | Session | Planned Start Date | Planned End Date | Schedule Start Time | Schedule End Time | SPOC | Overall KT Progress(%) | Is recording Available for the KT Session? | Location link of Recording | Technical docs Repositiry | Status/Remarks
Shared Services Cloud | Client | TechM Cloud Team | Project Overview | Understand Current Environment and Infrastructure Walk through of Documents Subscription details Environment details Application Details Vendor Support & other like shift support details Scope of work with respect to Azure Cloud | Session1
|  |  | Azure/Platform | HLD of Azure environment | Session2
LLD of Azure environment
SOP Docs for Azure environment
Runbooks for Windows/Linux environment
|  |  | Azure | Azure Introduction and overview | Session3
Security
Virtual Instances
Documentation
Disaster Recovery
Vendor Management
|  |  | Azure Native Monitoring | Collect- Metrics, Log Analytics Visualize and analyze- Dashboard Alert configaration based on the Threshold How is server monitoring performed? What all is being monitored currently and what is the priority of different types of alerts. Any exclusions from monitoring Various thresholds for monitoring. Any exceptions to monitoring? Any console available for team to view live alerts POC for alerts and standard procedure/processes to be followed in case of P1 & P2 issues Are monitoring tickets generated automatically? Process/doumentation for handling monitoring alerts | Session5
|  |  | Azure Key Vault/Encryption/Service accounts | Where are these services account used is it for any application or servers. | Session6
Will require the services account details with credentials.
Details on Key vaults and encryption used in environment
Do we have any specific group policy for these service account
Please provide the naming convention used for the service accounts.
|  |  | Azure Backup | Back up a Virtual Machine Recovery services Vault Backup policy Backup retention policy Backup and recovery (tools and technology being used) Backup and restore process | Session7
|  |  | Azure Network | Landing Zone, Bastion Host, Jump Server, Network Connectivity & high level Architecture VPN & Firewall Gateways,Connections, Network vendor and line details | Session8
|  |  | Storage | Storage Overview Blob storage Storage account Encription W.r.t Bring your own key (BYOK) Storage account access methodology(Shared service access storgae account, Secret Keys etc..) Log Analytics Details | Session9
|  |  | Compute | Virtual Machines Deployments & other details,Vnets,Subnets,Azure load Balancer..etc Virtual Machine scale sets AKS | Session10
|  |  | Azure Security Center | Policies, Score, Day to day jobs | Session11
|  |  | Risk Identified | Risk tracker
|  |  | SIP and Value added already done | Tracker of SIP and Value added
|  |  | DR / BCP/ Resillence | RPO / RTO values / Default RPO / RTO Values | Session13
DR Sites / How DR is done / Frequencey / DR Drill
Application participating in DR
Recovery Time objective / Recovery Point Objective of DR applications
SLAs during DR period
Is DR testing done on every new application roll-out (specific to that application)
Windows Infrastructure services or Application running on Windows that are always active in DR
Existing Issues, Risk and Gaps with DR and BCP
DR Locations for various sites
|  |  | Vendor Management | Vendor Management process/Contract document,Discussion with Other App vendors/Suppliers | Session14
Vendor Contacts & SLA
Vendor Support Escalation Matrix
|  |  | License Management | When servers are decommissioned, how the License are retained, Briefly understand the process,Do we use Azure BYOL or use the OS licensing from azure,if we use BYOL , please provide details for the KMS server in use. | Session15
Contact details of License owners, Globally, License/Certificates Management
How the new software purchase model works
|  |  | Azure Patch Management if applicable required (OS patching will be taken care by Infra team) | Overview of Patching tool, function and dependecies Patch mgmt process-Decision on installation of patches, Selection of Patches / Reporting,Troubleshooting with Installed patches, Troubleshooting of different Error Codes if problem is related to windows client Patch process with Release Management team Patch server Administration / Script Customisation Server grouping towards patch Presence of Global Patch servers Patch Architecture Pre and Post deviation process in Patching Support team and Security team handshake process Exceptions on Patching process How windows clusters are being patched. Frequency of patch roll-out Sequence of Patch installation (Non Prod , Prod) Do you have any requirement that one part of the production environment should be patched before another? Presence of Test environment for Patches How the Patches are assessed Emergency Patch deployment process Server Downtime window How the Patch roll back is done How the Server restart is stopped / halted towards Server patching What are GPO and Registry changes done on clients for Patch pro cess Patch calender for Critical and no Critical Infrastructure (Prod and Non Prod) | Session16
|  |  | Process | Any process being followed for Capacity Management | Session17
Incident Management
Change Management
CMDB Management
Problem Mangement
Escalation Matrix
OnBoarding / Offboarding Management
Documentation
High Level overview of IM/CM/PM Process
Change Communication Process
Change Control Approval (CAB) Details
Incident Response/Resolution Time-lines
Change Freeze Calendar
Daily/Weekly/Quarterly/Yearly Review Meetings
Process to handle planned down-time like Patching and Rebooting of Tools Services
Tools Server and Services Restart policies for Scheduled Maintenance
SEV1/SEV2/SEV3/SEV4 Ticket Discussion
Current Outage Handling Process for these Tools
All Critical SEV1/SEV2 ticket dump analysis with permanent resolution (RCA Documentation)
List of Segregated Critical Tools (per SLAs (Gold,Silver,Platinum Standards)) (If Applicable)
Details of SOX/Other Compliance & Audit
Current procedure to demonstrate data to the auditor on quarterly or on Demand basis for all SOX compliance Tools/Data
Special Event Coverage for these Tools (If Applicable)
Overview on existing Problem management process
Known/persistent issue details;Major Infra agents issues that occurred frequently
Process of identifying problem from repetitive Incidents
Escalation process after Identifying problem
Overview of Service request and workflow process
|  |  | Antivirus | Please provide the details of the Antivirus used for the environment | Session18
Where is Antivirus master server located.
Who is Currently managing the Antivirus.
What is the version and Antivirus Update Strategies
How are the new build servers getting the Antivirus installed.
How is the Antivirus Licensing Managed for Client as well for the servers.
How is the Antivirus Licensing Managed for Client as well for the servers.
|  |  | Application Mappings / Vendor | Deepdrive on Applications installed on Windows | Session19
Understand Application Environment / Application mapping with Inventory
Schematic Diagrams of Application
Application owner info / Escalation Matrix / Installation procedures
Scripts running on Windows / File Exclusion for AV
Challenges / Leagacy apps / Outage Window
Business Slowdown / Peak Business window
|  |  | Tools & Scripts | System Management Tool,Maintaining & troubleshooting scripts | Session20
Password Management Tool
Server Monitoring tools & Threshold Prameters configured
Backup Tools /Agent installed & support scope of wintel
Tool used for Vulnerablility scanning and dependency of wintel track
Health check Procedures/Documents/Scripts
Tools useded in day to day operations;Performance and Fine Tuning of Servers : Process Performance and Fine Tuning of Servers : Tools used Reports generated
Patch Management Tool Wintel Scope
Server Build Image build tool & Wintel Scope
Network Management Tools like (SMS/SCCM) existance & Wintel track scope
Standard scheduled /batch job over wintel server
|  |  | Azure IP/DHCP Management | Existing IP/DHCP inventory | Session21
IP address and reservation details/process
Network team escalation matrix
Default lease duration
Documentation of IP management
|  |  | Inventory Classification | Server naming conversion segment wise | Session22
Baseline Inventory list with complete server details (App/owner/warranty)
Risk and issues with respect to Asset
|  |  | OS Admin Task related to cloud | Introduction and overview Inventory Architectural & Design Overview of Wintel/Linux Environment Business Applications and Wintel/Linux Environment Dependencies Inventory collection / CMDB Discussions (H/W & OS Landscape) Existing Critical Windows Runbook and SOPs Understanding the Team Structure; Roles and Responsibilities Understanding the Risk/Issue/Assumption/Dependencies for on-going support infrastructure (KEDB) Discussion on Various Tools (scripting/ automated) in use Software/ OS Repository Details Password details (Shared/standalone) Tool used for Password Management Overview on Event notification tools and procedures Customer Escalation Matrix Known/persistent issue details Please provide the naming convention for the servers that are build. Do we have the Images for the Linux and Windows VM's. Do we update the image every 2 months with the latest patches and maintain a versioning for the same. Are we following all CIS standard. Is the image hardening applied on the VM Image or they are pushed by GPO once the server is built and joined to domain. Server domain joining procedure Provide the extract of the policy which is set up. Are there any specific application ports and protocol being open/closed using the policy. Do we have any specific requirments for the application of the Hardening standards. Server Installation Procedure & checklist Standard followed for OS configurations (Partioning/ Page file) File system Configuration Operating System Customization for Application Startup & Shutdown scripts setup & administration Complete Server Configuration document - Checklist Compliance Management/Server Hardening Tools Installation / Agent Local Administrator name and other Local account names Server Build and Configuration standards (Comissioning /Decomissioning) Server Rebuild in the event of Failures (Refernce docs/Dependency/Process),DR / BCP/ Resillence,Windows Patch Management | Session23